## Sheet1
	Assigned Task	Completed
Day 0
Abhishek	Egit installation, discuss project statement	Yes
Ayush	Discuss project statement	Yes
Indranil	Discuss project statement	Yes
Parag	Egit installation, discuss project statement	Yes
Srishti	Egit installation, discuss project statement	Yes
Sushrut	Discuss project statement	Yes
Gaurav	Egit installation, discuss project statement	Yes
Vatsala	Egit installation, discuss project statement	Yes

Day 1
Abhishek	Understand requirements, discuss class diagram	Yes
Ayush	Understand requirements, discuss class diagram	Yes
Indranil	Understand requirements, discuss class diagram, make ERD	Yes
Parag	Understand requirements, discuss class diagram	Yes
Srishti	Understand requirements, discuss class diagram	Yes
Sushrut	Understand requirements, discuss class diagram	Yes
Gaurav	Understand requirements, discuss class diagram	Yes
Vatsala	Understand requirements, discuss class diagram	Yes

Day 2
Abhishek	Work on sample rest client class	Yes
Ayush	Work on wiring, front end GUI and logic to interact with rest service	Yes
Indranil	Create class diagram, ETL, generated SSIS package and linking MS SQL server and Mysql	Yes
Parag	Create class diagram, Work on session bean implementation	Yes
Srishti	Create class diagram, Work on session bean implementation	Yes
Sushrut	Work on rest client class	Yes
Gaurav	Work on wiring and rest client class	Yes
Vatsala	Prepare docs, work on rest wiring, entity, session bean, and rest implementation	Yes

Day 3
Abhishek	Study and work on rest classes	Yes
Ayush	Work on sending different data formats to rest, UI design	Yes
Indranil	Work on database wiring, actual database modelling	Yes
Parag	Work on main project session bean implementation	Yes
Srishti	Work on main project session bean implementation	Yes
Sushrut	Work on main project session bean implementation	Yes
Gaurav	Study and work on rest classes	Yes
Vatsala	Work on remote database wiring, run end-to-end application	Yes

Day 4
Abhishek	Work on writing rest classes for actual database	Yes
Ayush	Work on sending different data formats to rest, UI design	Yes
Indranil	Generated actual database	Yes
Parag
Srishti	Work on main project session bean implementation	Yes
Sushrut
Gaurav	Study and work on rest classes	Yes
Vatsala	Work on creating entity beans for actual database	Yes

Day 5
Abhishek	Work on writing rest classes for actual database
Ayush	Work on sending different data formats to rest, UI design
Indranil	Generate data for new filter columns in database
Parag	Work on main project session bean implementation, write unit tests
Srishti	Work on main project session bean implementation, write unit tests
Sushrut	Work on main project session bean implementation, write unit tests
Gaurav	Study and work on rest classes
Vatsala	Merge entity bean, session beans and rest for demo